## Sheet1
Functionalitate | Prioritate Functionalitate | Task | Estimare Task | Status | Popescu Sabin | Patru Manuela
User registration | 1 | implementare interfata grafica | 5h | In progres |  | x
User registration | 1 | validare parola si nume utilizator | 7h | In progres | x
User registration | 1 | creare buton "Register" | 5h | In progres |  | x
Log in | 2 | implementare interfata grafica | 3h | In progres |  | x
Log in | 2 | validare nume utilizator si parola | 4h | In progres | x
Log in | 2 | creare buton "Log in" | 3h | In progres |  | x
Delete account | 6 | implementare interfata grafica | 7h | In progres | x
Delete account | 6 | stergere cont | 6h | In progres | x
Delete account | 6 | creare buton "Delete account" | 5h | In progres |  | x
View all champions | 0 | implementare interfata grafica | 7h | In progres | x
View all champions | 0 | afisarea tuturor campionilor | 5h | In progres | x
View all champions | 0 | creare buton "Champions" | 6h | In progres |  | x
View all skins | 0 | implementare interfata grafica | 7h | In progres | x
View all skins | 0 | afisarea tuturor skin-urilor | 5h | In progres | x
View all skins | 0 | creare buton "Skins" | 5h | In progres |  | x
View all items | 0 | implementare interfata grafica | 7h | In progres |  | x
View all items | 0 | afisarea tuturor itemelor | 5h | In progres |  | x
View all items | 0 | creare buton "Items" | 6h | In progres | x
View all runes | 0 | implementare interfata grafica | 7h | In progres |  | x
View all runes | 0 | afisarea tuturor runelor | 5h | In progres |  | x
View all runes | 0 | creare buton "Runes" | 5h | In progres | x
Create Matsrey 5/6 list | 7 | implementare interfata grafica | 7h | In progres |  | x
Create Matsrey 5/6 list | 7 | creare liste maiestrii | 5h | In progres | x
Create Matsrey 5/6 list | 7 | creare butoane "Create Matery 5/6 list" | 6h | In progres |  | x
Add champs to the mastery 5/6 list | 8 | implementare interfata grafica | 7h | In progres | x
Add champs to the mastery 5/6 list | 8 | creare buton "Add champ to the mastery 5/6 list" | 6h | In progres |  | x
Add champs to the mastery 5/6 list | 8 | selectare campion din lista de campioni | 6h | In progres |  | x
Add champs to the mastery 5/6 list | 8 | creare buton "Add" | 5h | In progres |  | x
Assign a number of tokens to a champion | 9 | implementare interfata grafica | 7h | In progres | x
Assign a number of tokens to a champion | 9 | creare buton "Assign a number of tokens" | 5h | In progres |  | x
Assign a number of tokens to a champion | 9 | asignare numar de jetoane | 3h | In progres |  | x
Delete a champion from a list | 10 | implementare interfata grafica | 7h | In progres | x
Delete a champion from a list | 10 | creare buton "Delete from list" | 5h | In progres | x
Delete a champion from a list | 10 | stergere campion din lista | 7h | In progres | x
Create setup | 11 | implementare interfata grafica | 7h | In progres |  | x
Create setup | 11 | creare buton "Create a setup" | 5h | In progres |  | x
Create setup | 11 | creare setup: campion-rune-iteme-maiestrie-numar jetoane | 7h | In progres | x
Create setup | 11 | creare buton "Save" | 5h | In progres | x
Update setup | 12 | implementare interfata grafica | 7h | In progres | x
Update setup | 12 | creare buton "Update a setup" | 5h | In progres |  | x
Update setup | 12 | modificare setup | 6h | In progres | x
Update setup | 12 | creare buton "Save" | 5h | In progres |  | x
Delete setup | 13 | implementare interfata grafica | 7h | In progres |  | x
Delete setup | 13 | creare buton "Delete a setup" | 5h | In progres |  | x
Delete setup | 13 | stergere setup | 6h | In progres | x
Delete setup | 13 | creare buton "Delete" | 5h | In progres | x
Live game | 5 | implementare interfata grafica | 7h | In progres | x
Live game | 5 | un utilizator poate urmari/afla cu cine joaca un meci la un moment dat | 9h | In progres | x
Live game | 5 | creare buton "Live Game" | 5h | In progres | x
Summoner's Stats | 4 | implementare interfata grafica | 7h | In progres |  | x
Summoner's Stats | 4 | creare buton "Summoner's Stats" | 5h | In progres |  | x
Summoner's Stats | 4 | vizualizarea diviziei/nivelului unui player in joc | 8h | In progres |  | x
Search | 3 | utilizatorul poate cauta in site prin bara de search. | 5h | In progres |  | x